## Slide 1: Preschool Development Grant Birth through Five Planning Grant Update
October 2023
Equity ● Quality ● Collaboration ● Community

## Slide 2: Activity I- Comprehensive Statewide B-5 Needs Assessment
1.1: Home Visitor Needs Assessment - Project Lead, Illinois Network of Child Care Resource and Referral Agency (INCCRRA): The home visiting needs assessment will build upon the previous PDG B-5 projects led by INCCRRA to inform how to best support the field and reduce staff turnover. INCCRRA will analyze home visiting salaries across program models and funding streams and hold focus groups with rural home visitors and Black Indigenous People of Color (BIPOC) home visitors to collect their thoughts and recommendations about salary increases, incentives, and credentials, pathways to home visiting as well as any related barriers. This important data from programs and professionals will inform how state agencies can work together to stem the Home Visitor workforce shortage.
Update:
  INCCRRA completed Round 2 of the focus groups and began completing the Round 3 focus groups in September 2023.
Equity ● Quality ● Collaboration ● Community

## Slide 3: Activity III-Family & Community Engagement
3.2 Assess and Align Capacity of Intermediary Structures - Project Lead, Wendy McCullough: Complete infrastructure mapping tasks; develop recommendations for engagement and outreach to families, communities and service providers.
Update:
  Wendy McCullough analyzed survey results and the results were reviewed with the Integration & Alignment Committee during the August meeting.
  A follow up meeting was held on September 27, 2023, to validate the directional recommendation and identify details and success factors to support the State’s implementation planning.
3.3 Developing framework for how the State will integrate family voice in policy-making - Project Lead, University of Chicago-NORC: Develop and implement a stakeholder engagement process (including focus groups and interviews) to authentically engage and elevate the voice of parents, providers, and communities in developing recommendations that prioritize equity as foundational to ECEC systems-building within Illinois.
Update:
  The NORC team drafted discussion guides and probing questions using a culturally responsive lens for the interactive focus group protocols and interviews with parents, providers, and key stakeholders (e.g., each discussion guide is customized for each audience – parents, providers, and stakeholders).
  NORC will facilitate a parent focus group during the 4th quarter.
Equity ● Quality ● Collaboration ● Community

## Slide 4: Activity IV-Support the B-5 Workforce & Disseminate Activities
4.1: Implementation of the Prior Learning Assessment - Project Lead, INCCRRA: Continue to implement the Mursion-based Prior Learning Assessment system through the first six months of 2023, after which funding from other sources will be used sustain implementation of the system. –
Update:
  INCCRRA is in the process of collecting data regarding learner proficiency and demographics and will share the information with the national data consultant for analysis. A final report will be written in December 2023.
Equity ● Quality ● Collaboration ● Community

## Slide 5: Activity V-Support Program Quality Improvement
5.1: Pilot Strategies for Inclusive Community-Based Early Childhood Special Education - Project Lead, Early CHOICES: Create public awareness materials, select appropriate models for testing, convene six community team conversions and test models, disseminate grants to three communities to pilot models, and provide consultation and training. –
  Update: Early CHOICES has identified three Community Inclusion Teams(CIT’s)-Collinsville, Quad Cities (Moline area) and Peoria County to participate in the project.
  The CIT’s presented an update to the Advisory Group and Early CHOICES has begun to draft a policy scan.
  During the 3rd quarter, Early CHOICES continued to interview programs to identify major cost components and drivers, and any policy changes necessary for communities to implement itinerant services.
5.3 Developing a Common Process to Identify English Language Learners -Project Lead, The Center: Resources for Teaching and Learning: Implement a common identification process across the mixed delivery system that will lead to the full integration of English learners into the B-5 ECCE system and equity improvements.
Update:
  Early Childhood Professional Learning (ECPL) hosted two kickoff webinars to provide an overview of the project with PFA community-based organizations.
  As of August 31, 2023, five CBOs had committed to participating in this project.
Equity ● Quality ● Collaboration ● Community

## Slide 6: No-Cost Extension
The Administration for Children and Families (ACF) will allow states who received the 2023 PDG B-5 Planning Grant and the 4 states that are in the 3rd year of their Renewal Grant to apply for a no-cost extension.
In accordance with 45 CFR §75.308(d)(2), a grant recipient may request a one-time extension of the project period up to 12 months.
  The recipient must submit the request at least 10 days prior to the end of the project period.
  An extension should not be requested simply to spend unobligated balances.
  The purpose of a no-cost extension is to complete existing activities in an approved application or amendment, not to spend unobligated funds or begin new activities that involve significant rebudgeting or change in scope.
ISBE will request a no-cost extension early November 2023.
Equity ● Quality ● Collaboration ● Community
Notes: Logic of November – October will be dominated by SAT performance levels, release of statewide report card.

## Slide 7: Questions
Equity ● Quality ● Collaboration ● Community
Notes: Logic of November – October will be dominated by SAT performance levels, release of statewide report card.

## Slide 8: Thank You
Equity ● Quality ● Collaboration ● Community
Notes: Logic of November – October will be dominated by SAT performance levels, release of statewide report card.